Subaward Processing Quick Reference Guide

| New Subaward New Subaward Create Create Assign Resources Assign Resources Plan Plan Initiate Initiate | - Subaward is a written agreement with a third party for the acquisition of services or goods, or for the conduct of prescribed activities or functions under an award. - Subaward Agreement is a document written under the authority of, and consistent with the terms and conditions of an award (a grant, contract or cooperative agreement), that transfers a portion of the research or substantive effort of the prime award to another institution or organization. - The subrecipient has responsibility for programmatic decision making and measurable performance requirements related directly to the Federal (prime) award. Subrecipients must adhere to federal compliance requirements. PROPOSAL PROCESSING - PI EVALUATES SUBRECIPIENT - Assess technical expertise and reasonableness of costs for subrecipient organization and key personnel. - PRINCIPAL INVESTIGATOR (PI) REQUESTS PROPOSAL PACKAGE FROM PROPOSED SUBRECIPIENT, TO INCLUDE - Statement of Work (SOW) - Budget and Budget Justification - Negotiated F&A and fringe rates - Any other documents required by UMASSD or sponsor - Signed Letter of Intent - PI PREPARES PROPOSAL, INCLUDING SUBAWARD - Include budget, budget justification, scope of work, Summary Disclosure Form, Proposal Routing Form and subaward (if any) paperwork in #2 - Include the subrecipient’s budget total as a single direct cost line item in UMASSD budget - Include other forms (e.g., biosketches, other support) as required by sponsor - Email everything to SPA for review - Complete application in Cayuse424, Fastlane or appropriate submission portal. When completed allow access to SPA in the system - Forward completed internal proposal paperwork to SPA Pre-Award Manager for review - SPA PRE-AWARD MANAGER REVIEWS AND APPROVES A PROPOSAL, INCLUDING SUBAWARD BUDGET AND VERIFYING THE RATES, IF APPLICABLE, FOR SUBMISSON TO SPONSOR SUBAWARD ISSUANCE - SPA PRE-AWARD AND SUBRECIPIENT MANAGER FOLLOWS UP WITH PI TO OBTAIN ANY ADDITIONAL DOCUMENTATION FROM SUBRECIPIENT - F&A rate agreement, if not previously obtained - Fringe rates agreement, if not previously obtained 6. SPA PRE-AWARD AND SUBRECIPIENT MANAGER FOLLOWS UP WITH AUTHORIZED OFFICIAL OF SUB TO OBTAIN ANY ADDITIONAL DOCUMENTATION FROM SUBRECIPIENT - Verifies current rates (F&A/Fringe) and requests revised budget if necessary - Secure revised SOW and requests revised budget if necessary - Human and/or animal subjects approvals, if applicable - Requests Subrecipient Profile Questionnaire for risk assessment, if not already on file at SPA - Single Audit certification, if subrecipient is not subject to Single Audit (if not already on file at SPA for the last fiscal year) 7. SPA COMPLETES FDP SUBAWARD AGREEMENT FOR SIGNATURES - Sends subaward paperwork (via email) to subawardee authorized official for review & signature - When subawardee authorized official signs, a fully executed subaward is sent to subawardee - PI is notified a subaward(s) has been executed and is prompted to create a Purchase Order (PO) for subaward invoicing Execute Execute 8. SPA PRE-AWARD AND SUBRECIPIENT MANAGER - Approves requisition for subaward - Files copy of subaward in primary award folder & in subaward folder - Creates an excel book to track subaward - Updates FFATA page in PeopleSoft - Reports FFATA, if required Control Control SUBAWARD MONITORING 9. PI MONITORS SUBRECIPIENT TECHNICAL PROGRESS Communicate & Report Communicate & Report Communicate regularly with subrecipient PI to monitor progress on the project - Monitor receipt of technical reports for timeliness and content - Communicate with SPA if changes need to be made to work statement, reporting requirements, budgeting 10. SPA PRE-AWARD AND SUBRECIPIENT MANAGER REVIEWS INVOICES - Are they arriving on schedule? Update & Track Update & Track Do they contain the right level of detail to allow adequate review? - Ensure all costs are allowable, allocable and reasonable - Ensure all costs were incurred within the period of performance of the subaward - Logs invoice in workbook - Emails invoice to PI for signature and authorization to pay - When signed, invoice is emailed to UMASSINVOICES for payment - Invoice is tracked until paid. Invoice filed in subaward folder and tracking sheet updated with payment information SUBAWARD AMENDMENT ISSUANCE 12. PI/DEPARTMENT SUBMITS A REQUEST TO CHANGE/AMEND SUBAWARD TO SPA - SPA Pre-award and Subrecipient Manager: - prepares Amendment and submits Amendment to subaward authorized official - sends PI and purchasing confirmation of amendment - files a copy of amendment in primary & subaward folders and updates log - SPA Post-award Grant Managers rebudget if necessary Close Close SUBAWARD CLOSE-OUT 14. SPA PREPARES SUBAWARD FOR CLOSURE - Obtain final invoice (marked FINAL) from subrecipient - SPA sends Close-out Certification to PI for completion. When received, Close-out certification and subaward submitted to Grant Manager with primary file - Subaward is closed in log, PeopleSoft and moved to closed awards 15. SPA POST-AWARD GRANTS MANAGER and GRANT ACCOUNTANT COMPLETE CLOSE-OUT |
| --- | --- |